2030 Plan

Final Version

“An ancient company with a modern purpose”

Background

1.	In 2030 the Worshipful Company of Weavers will be celebrating the 900th Anniversary of its mention in the Pipe Roll of 1130 (The 900th celebration will coincide with the 875th anniversary of the Weavers' earliest surviving Royal Charter). Our 900th Anniversary program will build on the Weavers' heritage as an ancient company with a modern purpose.  We wish to raise the profile of the UK Textile Industry, supporting young people entering the industry, whilst highlighting the charitable contribution of the wider Livery movement and the vibrancy of the City of London, of which we are an active part.  If we can use our 900th Anniversary to catalyse additional investment and opportunities within the UK textiles industry, that would be one of our positive legacies.

Global & Social Context

(See PESTLE and SWOT at Appendix 1)

2.	In 2030, there will be many differences to today, the majority of which are unpredictable. The key factors will be:

- A Labour government which will require Company to focus on its charitable activities rather than history and fellowship or large extravaganza.

- It is likely that the Ukraine conflict will be ongoing and there will be tension in the Middle East , which will divert attention and could impact global economy.

- The Lord Mayor maybe the current Ward of Cheap Alderman.

- The UK Textile Industry & UKFT will continue to need support.

- Make use of the Anointing Screen.

Major Anniversaries & Events in 1130

(See Appendix II)

3. 	The major event in 2030 will be the FIFA World Cup which will also be the 100th Anniversary of the first one. In relation to the Company, it should be noted that it will be the 25th Wedding Anniversary for the King and Queen. The Company could consider a suitable weaver related gift.

Vision

4.	That the country recognises, appreciates and supports the value and importance of the UK Textile Industry.

Mission

5.	The mission of the 900th anniversary celebrations is to gain the maximum possible exposure to and support for:

- The UK Textile Industry.

- The Weavers Company contribution to the textile industry, its charitable and educational activities.

- The role of the Livery Movement and the City of London Corporation.

In order to demonstrate the value of the UK Textile Industry and the Livery Movement.

End State

6. 	A successful campaign will result in the following goals being met:

- A wider and better understanding of the UK Textile Industry in order to attract new and diverse talent – need SMART objectives.

- A wider and better understanding by opinion formers (both national and international) and the general public on the role of the Livery Companies and the Weavers in particular which will enhance the effectiveness of the Company’s programmes – need SMART objectives.

How will this be measured – tied to paragraph above

7.	This will be measured through (need professional support)

Concept

(See Appendix III)

8.	Over the next five years the Company will deliver a major event each year that will not only support the areas in which it works but use these events to support the vision.  This will be achieved by delivering a major event each year up to a large event or series of events in 2030. The process has already started, and by year will be:

- 2025: Charitable Grants Summit (completed).

- 2026: Book Launch.

- 2027: Exploit first graduation from Leeds BSc course which will coincide with ITMA. The Company will support a reception at ITMA to assist BTMA.

- 2028: Sponsor the Weavers Conference at Manchester University of Science which will                                                     include a reception for all weavers’ scholars/ ETWS and industry. This will   coincide with Primary Schools Textile competition launch

- 2029: Textile exhibition in Guildhall Gallery which would include the Anointing Screen and all the Company Wall Hangings.

Guildhall Dinner for all livery masters and clerks.

Float Lord Mayors Show.

- 2030: United Guilds Service (UGS), create choral anthem.

Textile Awards – presence of the King and present gift and will include the winner of                                                                           schools competition.

Criminal Justice Intervention (may happen earlier).

The ambition in 2030 will be to either hold a large event/occasion within the City with the following criteria:

- Open to public.

- Able to be broadcast.

- Centred on Textile Industry both forward looking and historical.

- Involve other Livery Companies and Corporation.

- Major partner, either individual or organisation.

In the background, the administrative committees will need to support these efforts in particular the Investments Committee will need to identifying suitable assets to be disposed off to support the financing of the events.

Tasks

9.	2030 Working Group.

- Coordinate and manage the plan.

- Plan and deliver the book launch.

- Manage the project to create a new Choral Anthem for the 2030 UGS.

- Plan and deliver the major 2030 event, likely to be based at London Museum.

In order to achieve the Company’s vision for 2030.

10.	Charitable Grants Committee. Deliver:

- A Criminal Justice Summit.

- A major intervention in the field of criminal justice which will inform future government policy by 2030.

in order to demonstrate the influence of the livery movement in the charitable sector.

11.	Textile Committee.

- In conjunction with Primary Schools Committee design a textile design competition.

- Support the book launch.

- Support BTMA to run a reception at ITMA 2027.

- Identify best location to host Weavers’ Industry Reception in 2028, likely to be Manchester Museum of Science.

- Commission a new wall hanging for unveiling at 2029 Textile Exhibition.

- Deliver a textile exhibition in the Guildhall Gallery in 2029.

- In conjunction with Wardens’ Committee design float for the Lord Mayor’s show in 2029.

In order to demonstrate the vibrancy of the UK Textile Industry and the Company’s support.

12.	Almshouse Committee.

- Create 25 year strategy for the Almshouse.

- Continue moves towards net zero.

In order to demonstrate company’s charitable commitments.

13.	Primary Schools Committee.

- In conjunction with Textile Committee design a textile design competition.

- Consider a suitable intervention for the supported primary schools in 2030.

In order to demonstrate company’s charitable commitments.

14.	Investments Committee

- Maintain current income levels.

- Be prepared to provide large cash injections.

In order to support Company’s ambitions.

15.	Selection Committee. Continue to:

- Recruit suitable individuals.

- Continue diversity efforts.

In order to support the company’s diversity initiatives.

16.	Wardens Committee.

- Form Committee for Company Ball in 2030.

- Support Textile Committee in designing Lord Mayor’s Show float.

In order to support the Company’s ambitions.

Already Programmed/Costed  Events

17. The following activities have already taken place:

- 2023: Book commissioned to celebrate both the history of the Company and the UK Textile Industry today.

- 2025: the Company will host a summit/conference with the Clinks charity. This will be focussing on the rehabilitation of women prisoners and specific challenges that will result from the proposed removal to custody for sentences of under a year. Beyond the opportunities for thought leadership and shared learnings, the Company will announce a project design phase to identify a winning consortium of professionals that will help it shape and deliver a significant criminal justice intervention in the years up to 2030. - Complete

- 2026: Book Launch,

COORDINATING ACTIVITIES

18.	Communications (in progress). The Communications plan has been created for both internal and external audiences.

- Internal. Internal Communications will be run by the Clerk in conjunction with the 2030 Working Group. They will ensure that all members of the Company understand the key messages so that they can also influence the external audience. The 2030 Working Group will coordinate and monitor all the 2030 tasks.

- External.

- Influence. An Influence plan for the Company needs to be produced which can be used for engaging potential supporters and key stakeholders. The Clerk will write to all Livery Companies in 2025 to explain the Company’s plans. - Done

- Media (in progress).  A professional Media plan needs to be produced in order to publicise the Company’s activities. The initial plan has been produced by PerceptionA.

- Book (in progress). A book is being produced which will be used to help educate/communicate with external organisations on the anniversary. It will act as an up market calling card, enabling any specific letter asking for support to be taken more seriously. The emphasis on the role of the book will be to make the book the standard work on Weaving /textile industry/role of Livery company.

Company Involvement

19.	All members of the Company will be involved in delivering this project.

19.	Media training will be provided for the 2030 Company Officers in 2029.

Budgets

20. 	Budget currently £20,000 per Annum.

21.	Outline Financial Plan. The projected costs are at Appendix IV. Costs will fall between two funds:

- General Fund. This will need additional funds from the Investment Committee.

- Millennial Fund. The Court has amended the objectives of the Millennial Fund to:

  - To build a significant new charitable fund by the Company's Millennium in 2130.

  - To make exceptional “one-off” charitable donations as decided by the Court which fall outside the scope or budget of the Textile, Primary Schools and Charitable Grants Committees in order to mark significant anniversaries for the Company.

This will be used to support the CGC activities.

Internal Company Activities

22.	This plan has not covered how the Company wishes to actually physically mark this anniversary, previous anniversaries have been marked by pieces of silver etc. The initial thought is to commission a painting of modern/traditional weaving.

23.	The 2030 Company Trip will be to Brussels which will be similar to the 1930 trip. The Clerk has written to the Anglo-Belgian society.

24.	The May Dinner in 2030 will be a celebratory ball.

25.	The Company has a barrel of Whisky at the Wolfburn Distillery.

Appendices:

I.	SWOT/PESTLE and Risk Register

II.	2030 Anniversaries and Events

III.	Campaign Plan

IV.	Budget & Costs